## 1. Transparency
2022-2023 Transparency and Integrity Action Plan of the City Hall of Tsageri Municipality
Direction I. Transparency
Goal 1. Improve the quality of transparency in the City Hall
Impact Indicator: Level of trust/satisfaction of local population
Objective 1.1. |  | Raise Awareness of Public Information in the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Percentage of public information requests that were satisfied |  | 85% | 100% |  | IDFI's annual FoI assessment
Compliance of proactively published information with the list provided by law |  | 47% | 100% |  | Local Self-Government (LSG) Index Assessment Results
Risks: |  | The Second wave of COVID 19 pandemic | Risk reduction mechanism |  | Conduct trainings in remote mode
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
1.1.1. | Organize training on public information for the heads of structural units of the City Hall of Tsageri Municipality | Percentage of heads of structural units of the City Hall of Tsageri Municipality who completed the training | Training attendance sheet | Administrative Unit |  | 2022-I | City Hall Budget
1.1.2. | Provide training on public information for the person responsible for publishing public information in the City Hall of Tsageri Municipality | Duration of the training and its topic | Training agenda | Administrative Unit |  | 2022-I | City Hall Budget
Objective 1.2. |  | Improve Public Information Proactive Disclosure Standard and Practice in the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Compliance of proactively published information with the list provided by law |  | 47% | 100% |  | Local Self-Government (LSG) Index Assessment Results
Open data publishing format |  | PDF, Excel | CSV, XML |  | Local Self-Government (LSG) Index Assessment Results
Risks: |  | lack of competent staff | Risk reduction mechanism |  | increase the competency of relevant staff
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
1.2.1 | Development of normative documents regulating public information requests and proactive disclosure | The document defines the structural units, terms, functions-duties and procedures responsible for issuing and proactively publishing public information. | Normative document of the City Hall | Administrative Unit |  | 2022- I | City Hall Budget
1.2.2 | Develop a guide / instruction on processing and publishing open data | Content of the document / instruction | Document / Instruction | Administrative Unit | Legal Unit | 2022-I | City Hall Budget
1.2.3 | Introduce the guide / instruction on processing and publishing open data to the City Hall staff | Percentage of the City Hall staff who are familiar with the guide / instruction | Training attendance sheet / list of participants | Administrative Unit | HR Unit | 2022-II | City Hall Budget
1.2.4 | Improve public information that is being proactively published on the City Hall website and publish all relevant data in open format | Local Self-Government (LSG) Index Assessment Results | LSG Index | Administrative Unit |  | 2022-III | City Hall Budget

## 2. Accountability
2022-2023 Transparency and Integrity Action Plan of the City Hall of Tsageri Municipality
Direction II. Citizen Engagement and Accountability
Goal 2. Improve the transparency quality of the City Hall of Tsageri Municipality and citizen engagement in decision-making process
Impact Indicator: Local population trust/satisfaction index
Objective 2.1. |  | Improve the Communication Practice with Citizens and Ensuring Their Engagement in Decision-making Process
Outcome Indicator |  | Baseline | Target |  | Verification Source
Usage index of Tsageri City Hall electronic services |  | 0 | 10 |  | Data processed by Tsageri City Hall
Share of decisions in which employee involvement was ensured in working group forms |  | 0 | 70% |  | Minutes of working group meetings
Risks: |  | COVID 19 pandemic | Risk reduction mechanism |  | Conduct meetings in remote mode
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
2.1.1. | Ensure proactive publication of information on registration of civil initiatives and decisions made at Tsageri City Hall | Published information on initiated initiatives and response to them | City Hall website / social page | Administrative Unit | Legal Support and Supervision Unit | 2022-I | City Hall Budget
2.1.2. | Raise population awareness of electronic services of the City Hall of Tsageri Municipality through social media and general assembly of settlement/meetings | Number of awareness-raising activities | City Hall social networks, meeting minutes | Administrative Unit |  | 2022-II | City Hall Budget
2.1.3. | Ensure the functioning of Tsageri City Hall electronic services | Online services work without interruption and instructions for using each of them are easily available on the website | Tsageri City Hall website | Administrative Unit |  | 2022-II | City Hall Budget
2.1.4. | Adopt a normative document on ensuring employees' involvement in decision-making process | Normative document defines rules and forms of employees' involvement in decision-making process | Normative document | Administrative Unit | Legal Support and Supervision Unit | 2022-I | City Hall Budget
2.1.5. | Allocate a relevant person to Tsageri City Hall to communicate with vulnerable groups | The relevant person, identified for dealing with vulnerable groups, is trained in the specifics of these groups | Normative document | Administrative Unit | Legal Support and Supervision Unit | 2022-III | City Hall Budget
Objective 2.2. |  | Support Population in Terms of Using the most Necessary and Demanded Services of the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Percentage of the most demanded services, which usage rules and procedures are clearly indicated on the City Hall website |  | 0 | 100% |  | Tsageri City Hall website
Risks: |  | Change in demand for services | Risk reduction mechanism |  | Conduct periodic electronic surveys and update the website accordingly
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
2.2.1. | Conduct a survey to identify the most demanded services of the City Hall of Tsageri Municipality (population survey and/or analysis of the data available at the City Hall) | The survey provides an opportunity to identify the most demanded services for the local population | Research document | Administrative Unit |  | 2022- III | City Hall Budget
2.2.2. | Visibly place information on the rules and procedures for using the most demanded services available on the City Hall website | The information about the most demanded services on the City Hall website allows one to use it without searching for additional information | City Hall website | Administrative Unit |  | 2022-IV | City Hall Budget
2.2.3. | Ensure electronic participation of citizens in City Council councils | Citizens can attend the meeting of the City Hall Councils electronically | Electronic platform used by City Hall (eg zoom) | Administrative Unit |  | 2022-II | City Hall Budget

## 3. Human Resource Management
2022-2023 Transparency and Integrity Action Plan of the City Hall of Tsageri Municipality
Direction III. Human Resource Management
Goal 3. Improve human resource management in the City Hall of Tsageri Municipality and promote employees' professional development
Impact Indicator: Satisfaction level of the City Hall of Tsageri Municipality employees
Objective 3.1. |  | Ensure the Rationalization of Human Resources and Employees' Remuneration
Outcome Indicator |  | Baseline | Target |  | Verification Source
Increased wage of Tsageri Municipality employees |  | Salaries determined in the City Hall are slightly higher than the minimum salaries provided by the Law "on Remuneration in Public Institutions" | Salaries of the City Hall employees correspond to the high or average amounts set by the law for remuneration in public institutions |  | City Hall staff list
Compliance of the structure / staff list of Tsageri Municipality with the findings of the functional analysis |  | N/A | N/A |  | City Hall staff list and functional analysis
Risks: |  | Cutting City Hall budget | Risk reduction mechanism |  | Review the need for program funding and mobilize finances, find donors
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
3.1.1. | Conduct functional analysis of Tsageri City Hall | Analysis is based on the Civil Service Bureau guiding principles for functional analysis | Functional analysis document | Administrative Unit | Legal Support and Supervision Unit | 2022-IV | City Hall Budget
3.1.2. | Define job descriptions and determine employees' salaries according to the findings of functional analysis | Job descriptions are in compliance with the findings of functional analysis and salaries are determined according to the job decriptions | Job descriptions | Administrative Unit | Financial Unit | 2023 - I | City Hall Budget
Objective 3.2. |  | Promote the Professional Development of Tsageri City Hall Employees
Outcome Indicator |  | Baseline | Target |  | Verification Source
Percentage of the City Hall of Tsageri Municipality employees who have participated in educational trainings relevant to them |  | 0 | 80% |  | Training attendance sheets, training agendas
Risks: |  | The Second wave of COVID 19 pandemic | Risk reduction mechanism |  | Use remote/online communication tools in implementation of educational trainings
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
3.2.1. | Conduct professional needs assessment of Tsageri City Hall employees | Number of City Hall employees who participated in the needs assessment process | Needs assessment document | Administrative Unit |  | 2022-I | City Hall Budget
3.2.2. | Plan-find professional activities according to the findings of the needs assessment | Conformity of the planned professional activities with the findings of the needs assessment | Plan of professional activities | Administrative Unit |  | 2022-II | City Hall Budget
3.2.3. | Implement professional activities for the City Hall employees according to the identified needs | Number of the City Hall employees who participated in educational trainings relevant to them | Training agenda, registration sheets | Administrative Unit |  | 2022- 2023 | City Hall Budget
3.2.4. | Develop an introductory manual for newly appointed employees | The principles and peculiarities of the City Hall activities are described in detail in the manual | Introductory manual | Administrative Unit |  | 2022-II | City Hall Budget
3.2.5. | Provide periodic meetings of City Hall staff with City Hall staff from other municipalities to share best practices | Number of meetings with City Hall staff of other municipalities | Meeting records | HR unit | Administrative Unit | 2022-2023 | City Hall Budget
Objective 3.3. |  | Ensure transparency of Tsageri City Hall personnel policy
Outcome Indicator |  | Baseline | Target |  | Verification Source
Information about all vacancies is published on the City Hall website and social network pages, as well as information on the progress of the competition and the final decision. |  | N/A | 100% |  | City Hall website and social network page
Risks: |  | Violation of personal data of contestants | Risk reduction mechanism |  | Disclosure of information in accordance with the Law on Personal Data Protection
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
3.3.1 | Adoption of an internal normative act on ensuring transparency of vacancies in Tsageri City Hall | The act sets out detailed instructions on the information to be published and the rules for its publication | Relevant normative act | Administrative Unit | HR Unit; Legal Unit | 2022-II | City Hall Budget
3.3.2. | On the website of Tsageri City Hall and Soc. Constantly updating the information on the web page regarding the existing vacancies, the results of the competition | Detailed information on current vacancies, competitions and results is published on the website and social network in a language easily understood by the user. | City Hall website and Facebook page | Administrative Unit | HR Unit | 2022-2023 | City Hall Budget

## 4. Ethics and Cor. Risk Reduc.
2022-2023 Transparency and Integrity Action Plan of the City Hall of Tsageri Municipality
Direction IV. Ethics and Corruption Risk Reduction
Goal 4. Establish high ethical culture and standards in the City Hall and reduce corruption risks
Impact Indicator: Increase of local population trust towards the City Hall of Tsageri Municipality
Objective 4.1. |  | Normativize and Introduce in Practice Ethical Norms and Rules of Disciplinary Proceedings of the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Trust index of the City Hall of Tsageri Municipality employees |  | N/A | 80% |  | Results of an anonymous employee survey
Detected violations and their response rate |  | N/A | 100% |  | Statistics compiled by the City hall
Risks: |  | N/A | Risk reduction mechanism
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
4.1.1. | Develop a code of ethics of Tsageri City Hall | The code of ethics covers issues such as prohibited gift, conflict of interests and etc. | Code of Ethics | Legal Support and Supervision Unit | Administrative Unit, Audit Unit | 2022-II | City Hall Budget
4.1.2. | Develop an explanatory document on the code of ethics of Tsageri City Hall | The explanatory document is detailed, includes specific examples and covers all issues defined by the code of ethics | Explanatory document | Legal Support and Supervision Unit | Administrative Unit, Audit Unit | 2022-IV | City Hall Budget
4.1.3. | Introduce the status of ethics officer in Tsageri City Hall | The status of an ethics officer is granted to a person who has the relevant knowledge, experience and trust f employees | Mayor's decree | Administrative Unit | Legal Support and Supervision Unit | 2022-III | City Hall Budget
4.1.4. | Develop a document on disciplinary liability and procedures | The document clearly defines the grounds and types of disciplinary liability and determines proportional sanctions | Mayor's decree | Administrative Unit | Legal Support and Supervision Unit | 2022-II | City Hall Budget
4.1.5. | Raise city hall employees' awareness on issues of ethics, disciplinary proceedings and whistleblower institute | Number of City Hall employees who are trained on the issues of ethics, disciplinary proceedings and whistleblower institute | Training agenda, training attendance sheet | Administrative Unit |  | 2023 I-IV | City Hall Budget
Objective 4.2. |  | Introduce Corruption Risk Assessment System in the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Percentage of corruption risk assessment in Tsageri City Hall |  | 0 | 70% |  | Data compiled by the City Hall
Risks: |  | Necessary funds deficit in case of need for involvement of external experts | Risk reduction mechanism |  | Find donors
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
4.2.1. | Develop corruption risk assessment methodology/guide | Document is based on local and international experiences | Corruption risk assessment methodology/guide | Audit Unit | Legal Support and Supervision Unit | 2023-II | City Hall Budget
4.2.2. | Introduce corruption risk assessment methodology/guide to the City Hall employees | Number of City Hall employees who are familiar with the corruption risk assessment methodology/guide | Meeting minutes | Administrative Unit |  | 2023-II | City Hall Budget
4.2.3. | Add corruption risk monitoring function to the audit unit functions | Corruption risk monitoring is described as on of the functions of internal audit unite | Mayor's decree | Administrative Unit | Legal Support and Supervision Unit, Audit Unit | 2023-II | City Hall Budget
Objective 4.3. |  | Strengthen the oversight mechanism in Tsageri Municipality City Hall
Outcome Indicator |  | Baseline | Target |  | Verification Source
Response rate for ethics violations at Tsageri City Hall |  | 0 | 100% |  | Data compiled by the City Hall
Risks: |  | N/A | Risk reduction mechanism |  | N/A
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
4.2.1. | Supervision of the observance of ethical norms has been added to the functions and responsibilities of the Audit and Inspection Service of the City Hall | The Statute of the Service clearly defines the functions and procedures related to the supervision of ethical norms | unit statute | Legal Support and Supervision Unit | Audit and Inspection Unit | 2022-III | City Hall Budget
4.2.2. | Training of Audit and Inspection Service Staff on Ethics, Supervision and Disciplinary Procedures | Number of service employees who have undergone relevant training | Training agenda, training attendance sheet | HR unit | Audit and Inspection Unit | 2022-II | City Hall Budget

## 5. Public Procurement
2022-2023 Transparency and Integrity Action Plan of the City Hall of Tsageri Municipality
Direction V. Public Procurement
Goal 5. Establish high standards of public procurement in the City Hall
Impact Indicator: Successfully implemented local projects
Objective 5.1. |  | Ensure efficient budget planning and spending by Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Positive conclusion of the Budget Commission |  | Budget Commission Negatively Evaluates Budget Planning and Expenditure Process | Budget Commission Positively Evaluates Budget Planning and Expenditure Process |  | State / Internal Audit Reports
Risks: |  | Contingencies during the budget year | Risk reduction mechanism |  | Minimize unforeseen costs through proper process planning
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
5.1.1. | Analysis of the conclusions of the State Audit Office and the municipal budget commissions | Services involved in the analysis process and steps planned according to the identified challenges | Minutes of the working group, document of analysis | Internal Audit and Inspection Service | Financial Service, Human Resources Service, Administrative Service, Procurement Service, Legal Support and Supervision Service | 2022-II | City Hall Budget
5.1.2. | 5.1.1 Implement appropriate measures based on the analysis document prepared under the activity | Compliance with the implemented measures. With the analysis of the conclusions of the Audit and Budget Commission | Document for analysis of the conclusions of the Audit and Budget Commission | Internal Audit and Inspection Service | Financial Service, Human Resources Service, Administrative Service, Procurement Service, Legal Support and Supervision Service | 2022-III - 2023-III | City Hall Budget
Objective 5.2. |  | Improve the Transparency of Public Procurement Process in the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Number of companies participating in tenders announced by Tsageri City Hall |  | 1-3 | 4-7 |  | Data compiled by Tsageri City Hall
Risks: |  | Lack of companies operating in Tsageri Municipality | Risk reduction mechanism |  | Find companies across the country; specify the estimated tender period in the annual plan; needs assessment of potential suppliers
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
5.2.1. | Proactively publish information on ongoing tenders | Share of tenders published on the website and social network of the City Hall | City Hall report; Report of internal audit unit | Administrative Unit | Economic Unit | 2022-2023 | City Hall Budget
5.2.2. | Proactive publication of information about completed tenders and their results Share of tenders | Share of tenders, the results of which are published on the website of the City Hall and on the social media page | City Hall website | Administrative Unit | Economic Unit | 2022-2023 | City Hall Budget
Objective 5.3. |  | Improve the Public Procurement Planning Process by the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Percentage of failed tenders |  | 1-3 | 4-7 |  | Data compiled by Tsageri City Hall
Risks: |  | Lack of companies operating in Tsageri Municipality | Risk reduction mechanism |  | Find companies across the country; specify the estimated tender period in the annual plan; needs assessment of potential suppliers
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
5.3.1. | Develop integrity risk assessment rules/methodology in procurement process | Conformity of risk assessment rules/methodology with the standards of OECD and UNDP | Mayor's decree on adopting rules/methodology | Procurement Unit | Legal Support and Supervision Unit | 2022-IV | City Hall Budget
5.3.2 | Introduce in practice the integrity risk assessment rules/methodology of procurement process | Percentage of public procurement during planning of which integrity risks were assessed | Document of integrity risk assessment in public procurement planning process | Procurement Unit | Economic Unit | 2022-2023 | City Hall Budget
5.3.3. | Introduce the practice of needs assessment of potential suppliers throughout the municipality and analysis of tender conditions | Number of potential suppliers whose needs were assessed and analyzed tender conditions | Document of potential suppliers needs assessment and analysis of tender conditions | Procurement Unit |  | 2022-IV | City Hall Budget
5.3.4. | Introduce in practice the proper market research during the procurement planning process | Percentage of public procurement made on the basis of proper market research | City Hall report; Report of internal audit unit | Procurement Unit |  | 2023 | City Hall Budget
Objective 5.4. |  | Improve Internal Control Mechanisms in Procurement Process in the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Percentage of infrastructural projects delivered without proper quality inspection |  | 40% | 0% |  | Reports of State Audit Office/Internal Audit Unit
Risks: |  | Deficiency elimination request ignore by companies | Risk reduction mechanism |  | Conduct mid-term inspection; use legal mechanisms
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
5.4.1. | Establish group in internal audit system monitoring the conditions of infrastructural facilities | Number and qualification of employees of structural unit, financial resource | City Hall Budget, job descriptions, staff list | Administrative Unit | Legal Support and Supervision Unit | 2022-II | City Hall Budget
5.4.2. | Carry out quality inspection of infrastructural facilities | Share of infrastructural projects which quality was assessed in accordance with contract requirements | Reports on inspection of infrastructural projects; reports of state audit office/internal audit unit | Internal Audit Unit |  | 2022-2023 | City Hall Budget
5.4.3. | Introduce an electronic monitoring mechanism for implementation of public procurement contracts | Share of contracts subject to electronic monitoring | Mayor's decree | Administrative Unit | Internal Audit Unit | 2023-I | City Hall Budget

## 6. Permits
2022-2023 Transparency and Integrity Action Plan of the City Hall of Tsageri Municipality
Direction VI. Permits
Goal 6. Facilitate the use of permitting services for Tsageri municipality population
Impact Indicator: Increased constructions in Tsageri Municipality
Objective 6.1. |  | Improve Permitting Service in the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Percentage of permits issued in accordance with the rule of using and registering-accounting permit licenses |  | 0% | 100% |  | Reports of state audit office/internal audit unit
Risks: |  | N/A | Risk reduction mechanism
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
6.1.1. | Analyze the rules of using and registering-accounting permit licenses | The analysis highlight the shortcomings of the existing rules and determines the issues of bringing them in compliance with the Georgian legislation | Analysis document | Unit of Infrastructure, Spatial Planning, Construction, Architecture and Monument Protection | Legal Support and Supervision Unit | 2022-III | City Hall Budget
6.1.2. | Normativize the rules of using and registering-accounting permit licenses | Conformity of the rules of using and registering-accounting permit licenses with Georgian legislation | Mayor's decree | Unit of Infrastructure, Spatial Planning, Construction, Architecture and Monument Protection | Legal Support and Supervision Unit | 2022-IV | City Hall Budget
6.1.3. | Introduce a survey of population satisfaction assessment with municipal services | Satisfaction assessment forms are developed and used in practice | Satisfaction Assessment Forms Analysis Document | Unit of Infrastructure, Spatial Planning, Construction, Architecture and Monument Protection | Administrative Unit | 2022-IV | City Hall Budget
Objective 6.2. |  | Simplify permit appeal procedure in the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Share of challenged permit decisions appealed electronically |  | 0 | 60% |  | Data compiled by the City hall
Risks: |  | Lack of popularity of e-services among the local population | Risk reduction mechanism |  | Raise public awareness of the service and encourage its use
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
6.2.1. | Publish on the City Hall of Tsageri Municipality website the information about the rules for issuing, using and appealing permits | Information about the rules for issuing, using and appealing permits is available on City Hall website | City Hall website | Unit of Infrastructure, Spatial Planning, Construction, Architecture and Monument Protection | Administrative Unit | 2022-II | City Hall Budget
6.2.2. | Introduce an electronic mechanism for appealing against permit decisions | The simplicity of use of electronic mechanism | City Hall website | Unit of Infrastructure, Spatial Planning, Construction, Architecture and Monument Protection | Administrative Unit | 2023-III | City Hall Budget

## 7. Internal Financial Control
2022-2023 Transparency and Integrity Action Plan of the City Hall of Tsageri Municipality
Direction VII. Internal Control
Goal 7. Ensure the efficiency of Internal Audit Unit in the City Hall of Tsageri Municipality
Impact Indicator: Increase the economy, efficiency and productivity of the City Hall of Tsageri Municipality and improve public finance management
Objective 7.1. |  | Strengthen the Internal Audit Unit of the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Share of internal audit staff who have undergone professional training |  | 0% | 60% |  | Reports of state audit office/internal audit unit
Risks: |  | Delays in staff training due to pandemic | Risk reduction mechanism |  | online courses
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
7.1.1. | Ensure normative and practical independence of the internal audit unit | Normative act contains a reference to the independence of the internal audit unit and the unit is ensured with adequate financial and human resources | Normative act of the City Hall / Assembly, City Hall staff list and budget | Administrative Unit; Economic Unit | Internal Audit Unit; Legal Support and Supervision Unit | 2022-III | City Hall Budget
7.1.2. | Ensure professional development of the internal audit unite employees | Share of internal audit unit employees who are trained | Training agenda; Registration sheet | Administrative Unit; Internal Audit Unit |  | 2022-III | City Hall Budget
Objective 7.2. |  | Improving the monitoring mechanism by Tsageri City Hall
Outcome Indicator |  | Baseline | Target |  | Verification Source
Share of in-depth audits performed by the Internal Audit and Inspection Service of Tsageri Municipality |  |  | 100% |  | Reports of state audit office/internal audit unit
Risks: |  | pandemic limitations | Risk reduction mechanism |  | online courses
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
7.2.1. | Carry out comprehensive monitoring of recommendation implementation by auditees inspected by the internal audit unit in previous years | The reports provide detailed information on objects and the recommendations implemented / not implemented as well as on measures taken by the City Hall | Monitoring reports on implementation of the recommendations issued by the internal audit unit | Internal Audit Unit |  | 2022-2023 | City Hall Budget
7.2.2. | Conduct in-depth audit checks by the internal audit unit | Internal audit unit reports reflect conclusions and recommendations about the financial management and control system as well as procurement | Internal audit unit reports | Internal Audit Unit |  | 2022-2023 | City Hall Budget
7.2.3. | Improving the monitoring of City Hall units | Deadlines for monitoring City Hall services have been set and monitoring forms have been developed | Internal audit unit reports | Internal Audit Unit |  | 2022-2023 | City Hall Budget

## 8. Legal Entities
2022-2032 Transparency and Integrity Action Plan of the City Hall of Tsageri Municipality
Direction VIII. Legal Entities Subordinated to the City Hall of Tsageri Municipality
Goal 8. Ensure the transparency of the activities of Legal entities subordinated to the City Hall of Tsageri Municipality
Impact Indicator: Increase the trust of local population towards Tsageri City Hall
Objective 8.1. |  | Effective Human Resource Management of Legal Entities Subordinated to the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Percentage of legal entities subordinated to the City Hall optimization of which was carried out in accordance with their activities' analysis |  | 0% | 100% |  | Tsageri City Hall report on the analysis of legal entities' activities
Risks: |  | N/A | Risk reduction mechanism
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
8.1.1. | Analyze the activities of legal entities subordinated to the City Hall | The analysis document identifies shortcomings/challenges and ways for their elimination | Tsageri City Hall reports on the analysis of legal entities' activities | Internal Audit Unit | Administrative Unit | 2022-IV | City Hall Budget
8.1.2. | Optimize human resources of legal entities in accordance with the activities' analysis | Decision on human resource optimization is in compliance with the analysis | Decision on human resource optimization | Administrative Unit | Internal Audit Unit | 2023-I | City Hall Budget
8.1.3. | Introduce the practice of conducting transparent, open competitions for employee recruitment in legal entities | Number of employees recruited by legal entities in 2021 - 2022, who passed a transparent open competition | City Hall report | Administrative Unit | Internal Audit Unit | 2022-2023 | City Hall Budget
Objective 8.2. |  | Improve Transparency in Legal Entities Subordinated to the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Compliance of proactively published information with the list provided by law |  |  |  |  | City Hall website
Risks: |  | N/A | Risk reduction mechanism
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
8.2.1. | Publish comprehensive information on Tsageri City Hall website about the legal entities | Share of legal entities subordinated to the City Hall about which the public information is fully published on the City Hall website | Tsageri City Hall website | Administrative Unit |  | 2022-II | City Hall Budget
8.2.2. | Train employees of legal entities subordinated to the City Hall on public information and open data | Share of legal entities employees of which are trained in public information and open data | City Hall report | Administrative Unit |  | 2022-IV | City Hall Budget
8.2.3. | Prepare and publish complete activity reports of legal entities subordinated to the City Hall | Share of legal entities annual reports of which are prepared and published | City Hall website | Administrative Unit |  | 2022-2023 | City Hall Budget
Objective 8.3. |  | Introduce Ethical Standards in Legal Entities Subordinated to the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Detected violations and their response rate |  | N/A | 100% |  | Data compiled by Tsageri City Hall
Risks: |  | N/A | Risk reduction mechanism
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
8.3.1. | Develop a code of ethics at legal entities under Tsageri City Hall | The code of ethics covers issues such as prohibited gift, conflict of interests and etc. | Code of Ethics | Legal Support and Supervision Unit | Administrative Unit, Audit Unit | 2022-IV | City Hall Budget
8.3.2. | Raise the awareness of the employees of legal entities subordinated to the City Hall on issues of ethics, disciplinary proceedings and whistleblower institute | Share of legal entities under Tsageri City Hall employees of which are trained on the issues of ethics, disciplinary proceedings and whistleblower institute | Training agenda, training attendance sheet | Administrative Unit |  | 2023 - II | City Hall Budget
Objective 8.4. |  | Improve Internal Control of Legal Entities Subordinated to the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Share of legal entities subordinated to the City Hall where internal control mechanisms are functioning |  | 0 | 100% |  | Statutes of legal entities
Risks: |  | N/A | Risk reduction mechanism
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
8.4.1. | Establish internal audit units at legal entities under Tsageri City Hall | Internal audit units of legal entities are ensured with adequate financial and human resources | Staff list, budget, statute | Administrative Unit | Legal Support and Supervision Unit | 2023-I | City Hall Budget
8.4.2. | Introduce internal control practice at legal entities under Tsageri City Hall | Share of legal entities where internal control was carried out by the relevant units | Training agenda, training attendance sheet | Legal Entities | Internal Audit Unit | 2022-2023 | City Hall Budget
Objective 8.5. |  | Establish a High Standard of Accounting Representative Expenses in Legal Entities Subordinated to the City Hall of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Share of legal entities subordinated to the City Hall where internal control mechanisms are functioning |  | 0 | 100% |  | Statutes of legal entities
Risks: |  | N/A | Risk reduction mechanism
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
8.5.1. | Develop a rule of accounting representative expenses in legal entities under Tsageri City Hall | The rule is in compliance with Georgian Legislation | The rule of accounting representative expenses | Internal Audit Unit | Legal Support and Supervision Unit | 2022-I | City Hall Budget
8.5.2. | Introduce in practice the rule of accounting representative expenses in legal entities under Tsageri City Hall | Percentage of legal entities where representative expenses are accounted in accordance with the relevant rule | City Hall report | Internal Audit Unit | Legal Entities | 2022-2023 | City Hall Budget
8.5.3. | Develop and discuss at companions' meeting limited liability companies' annual financial statement and planned budget for the following financial year | Percentage of limited liability companies under Tsageri City Hall financial statement and planned budget of which are developed and discussed at companions' meeting | City Hall report, report of limited liability companies | Internal Audit Unit | Limited Liability Companies | 2022-2023 | City Hall Budget
objective 8.6. |  | Improving the state procurement of legal entities under the management of Tsageri Municipality
Outcome Indicator |  | Baseline | Target |  | Verification Source
Percentage of legal entities under the management of Tsageri City Hall, in which risk assessment is carried out during the procurement process |  |  | 100% |  | reports of legal entities
Risks: |  | N/A | Risk reduction mechanism
N | Activity | Output Indicator | Verification Source | Responsible Structural Unit | Partner Structural Unit | Term of Implementation (year, quarter) | Funding Source
8.6.1. | Introduction of risk assessment in the procurement process in the legal entities managed by Tsageri City Hall | The orders of the relevant legal entities provide for a detailed rule of risk assessment in the procurement process | Orders of relevant legal entities | Procurement Service, Administrative Service | Legal Support and Supervision Service | 2023-II | City Hall Budget
8.6.2. | Procurement plans and reports for legal entities managed by Tsageri City Hall are published on websites | Percentage of legal entities that publish procurement plans and reports | Websites of legal entities / City Hall | Administrative Service | Legal Entities | 2022-2023 | City Hall Budget